PES UNIVERSITY • DEPT. OF COMPUTER SCIENCE AND ENGINEERING

Lab 2: Agile Backlog Creation & Sprint Simulation in Jira

| Student Name: Nagashri R Patil | SRN: PES1UG24CS289 |
| --- | --- |
| Problem Statement: #43 – Feature Flag & Dynamic Config | Course: Software Engineering Lab (Lab 2) |

Master Laboratory Report combining Epics Architecture, User Stories Catalog, Sprint Simulation, Burndown Analytics, and Reflection Questions.

1. Epics Architecture

| Epic ID | Epic Summary | Scope | Traceability |
| --- | --- | --- | --- |
| FFM-EPIC-1 | Flag Lifecycle & Metadata | Flag CRUD, metadata, multi-env overrides | FR-002, FR-004, UC-01, UC-04 |
| FFM-EPIC-2 | Targeting & Percentage Rollout | Deterministic hashing, attribute targeting | FR-001, FR-003, UC-02, UC-03 |
| FFM-EPIC-3 | Governance, Approval & Audit | Approval gate, visual diff, audit logging | UC-06, UC-07, NFR-002 |
| FFM-EPIC-4 | Low-Latency Evaluation & SDK | Sub-15ms p95, real-time WebSocket sync | FR-005, NFR-001, UC-05, UC-03 |

2. User Stories Catalog (10 Stories)

| ID | Epic | User Story Statement | Priority | Pts | Sprint | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- | --- |
| US-01 | FFM-EPIC-1 | As a Software Engineer, I want to create a feature flag with a unique key, description, and default state, so that client apps can reference the flag unambiguously. | High | 3 | Sprint 1 | Pass: Duplicate key triggers 409 conflict; unique key registers < 2s. Fail: Duplicate keys accepted. |
| US-02 | FFM-EPIC-2 | As a Software Engineer, I want to configure a percentage rollout (0-100%) based on a deterministic hash of user IDs, so that I can gradually roll out features and limit blast radius. | High | 5 | Sprint 1 | Pass: 25% rollout allocates 25% (±2%) of 10,000 simulated IDs; hash mapping is strictly deterministic. Fail: User changes cohort across evaluations. |
| US-03 | FFM-EPIC-2 | As a Software Engineer, I want to evaluate user targeting rules for specific cohorts, so that targeted users receive early feature access. | High | 5 | Sprint 1 | Pass: User matching targeted attribute receives true; non-targeted user receives fallback. Fail: Non-targeted user receives feature. |
| US-04 | FFM-EPIC-4 | As a Software Engineer, I want the evaluation API to execute in under 15ms, so that embedding flag checks into critical paths adds negligible latency. | High | 8 | Sprint 1 | Pass: p95 latency under simulated peak load is < 15ms; in-memory cache lookup avoids disk I/O. Fail: Evaluation p95 exceeds 15ms. |
| US-05 | FFM-EPIC-4 | As a Client SDK Developer, I want the SDK to maintain a local in-memory cache with fallback defaults, so that network partitions do not break host application features. | Medium | 3 | Sprint 1 | Pass: In-memory evaluations return in < 1ms during offline conditions; graceful fallback. Fail: Application blocks on network drop. |
| US-06 | FFM-EPIC-1 | As a Software Engineer, I want to define environment-specific overrides (Dev, Staging, Prod), so that I can test flags in lower environments without exposing code in Prod. | Medium | 5 | Sprint 2 | Pass: Prod override set to OFF while Staging is ON returns false for Prod and true for Staging. Fail: Overrides leak between environments. |
| US-07 | FFM-EPIC-3 | As a Software Engineer, I want to save changes as pending drafts and preview a visual diff, so that I can verify proposed modifications before requesting approval. | Medium | 3 | Sprint 2 | Pass: Draft changes do not alter runtime configurations; diff clearly highlights altered rules. Fail: Draft changes alter live evaluations. |
| US-08 | FFM-EPIC-3 | As a Release Manager, I want to review, approve, or reject pending flag changes with validation checks, so that invalid configs never reach production. | High | 5 | Sprint 2 | Pass: Only authenticated Release Managers can publish; invalid rules (rollout >100%) rejected. Fail: Unauthorized user publishes changes. |
| US-09 | FFM-EPIC-3 | As a Release Manager, I want all configuration changes logged in an immutable audit trail with one-click rollback, so that actions are auditable and regressions revert instantly. | High | 5 | Sprint 2 | Pass: Tamper-proof audit record created for every publish; one-click rollback restores prior state < 3s. Fail: Change occurs without audit entry. |
| US-10 | FFM-EPIC-4 | As a Client SDK Developer, I want updated flag states streamed via WebSockets in real time, so that clients update within 5 seconds without redeployment. | High | 5 | Sprint 2 | Pass: 95% of active SDK connections receive updates within 5s; automatic reconnect upon drop. Fail: Clients take > 30s to synchronize. |

3. Reflection Questions

1. Did your estimations reflect the actual effort?

Yes. Relative estimation using the Fibonacci sequence accurately captured development complexity, technical risk, and testing effort. Low-uncertainty CRUD items (e.g. US-01, 3 pts) progressed quickly without blockers. Algorithmic stories (e.g. US-02 deterministic hashing and US-09 cryptographic audit logging, 5 pts each) accounted for statistical cohort validation and transaction integrity testing. High-risk performance engineering (US-04 sub-15ms evaluation latency, 8 pts) correctly mirrored the iterative profiling, memory caching, and benchmark tuning needed to fulfill NFR-001. Abstracting effort into story points rather than calendar hours protected the team from false precision and Parkinson’s Law.

2. Was your backlog well-prioritized?

Yes. Backlog prioritization followed architectural dependency sequencing and risk-reduction principles. Core flag creation (US-01) and deterministic evaluation (US-02, US-03) were scheduled at the top of Sprint 1 because downstream approval gates and WebSocket sync require a stable evaluation core to operate upon. Furthermore, scheduling the high-risk performance optimization (US-04) in Sprint 1 eliminated architectural risk early. Enterprise governance, environment isolation, and real-time streaming were layered cleanly in Sprint 2, creating a resilient MVP progression.

3. How did your simulated sprint align with your plan?

The simulated sprints closely matched planned execution. In Sprint 1, 24 planned points were delivered across 5 user stories with zero scope creep. In Sprint 2, all 23 points were completed. Pacing was disciplined: smaller 3-point stories moved to Done early in both sprints, while complex 5-point and 8-point items progressed through comprehensive unit and load verification before transitioning to Done by Day 5. All sprint boundaries were protected against unplanned scope injections.

4. What insights did the burndown chart give about your team's capacity?

Jira's Burndown Chart revealed three key operational insights: (1) Predictable Capacity: Completing 24 points in Sprint 1 and 23 points in Sprint 2 established that the team has a reliable, sustainable velocity of ~23–24 points per 1-week sprint. (2) Story Sizing & Burndown Trajectory: Large work items (e.g. 8-point US-04) create step-like burndown plateaus because points only burn upon complete verification. Decomposing 8-point stories into smaller 3-point slices in future sprints will yield a smoother burndown curve. (3) Discipline & Zero Scope Creep: The absence of upward spikes on the remaining values line confirmed strict sprint backlog discipline without uncommitted task creep.